## All Tickets
Ticket ID | Epic | Title | Type | Points | Summary | Acceptance Criteria | Dependencies | PRD Section | Notes
DASH-1 | Phase 1: Backend Foundation & P1 Polish | [BE] Dashboard service layer and all P1 endpoints | Backend | 8 | Create the dashboard service layer in fidesplus (Routes → Services → Repositories → Models) and implement all endpoints the P1 frontend already calls: GPS posture (4 dimensions), priority action queue, trends/sparklines, DSR summary, system coverage summary, and agent briefing. The frontend types and RTK Query hooks are already defined — this ticket makes them real. | GPS Posture (GET /api/v1/plus/dashboard/posture): • Returns PostureResponse: score (0-100), band, diff_percent, diff_direction, per-dimension breakdown • 4 dimensions: Coverage (20%) via StagedResource + MonitorSteward, Classification Health (15%) via StagedResource.classifications confidence + staleness, DSR Compliance (15%) via PrivacyRequest overdue/SLA/manual steps, Consent Alignment (15%) via Consent + ConsentRequest opt-in rates • Bands: 0-39 critical, 40-59 at_risk, 60-79 good, 80-100 excellent • Diff compares to 7 days ago Priority Actions (GET/PATCH /api/v1/plus/dashboard/actions): • Paginated PriorityActionsResponse with ?dimension= filter • Generates from: unreviewed classifications, overdue/approaching DSRs, systems without steward, consent anomalies, assessments needing review • Severity = regulatory exposure × time sensitivity × blast radius • PATCH /{actionId} for snooze/complete/dismiss with persistent state Trends (GET /api/v1/plus/dashboard/trends): • ?period=30d¦60d¦90d, returns TrendsResponse with history arrays for GPS, DSR volume, system coverage, classification health • <2s response for 90-day lookback DSR Summary (GET /api/v1/plus/dashboard/privacy-requests): • active_count, statuses breakdown, overdue_count, sla_health by action type System Coverage (GET /api/v1/plus/dashboard/system-coverage): • total_systems, fully/partially/unclassified, without_steward, coverage_percentage Agent Briefing (GET /api/v1/plus/dashboard/agent-briefing): • Briefing text + quick_actions from EventAudit delta since last login • V1: deterministic templates, persona-aware • Tracks user last login (new column or table) | None | §4.0-4.5 (P1 components) | Critical path — all Phase 1 FE work depends on this. Frontend types in dashboard.slice.ts are the contract.
DASH-2 | Phase 1: Backend Foundation & P1 Polish | [FE] Replace mock handlers with live API integration | Frontend | 5 | Wire all P1 dashboard components from MSW mocks to real backend endpoints. Reconcile type mismatches between frontend types and actual API responses. | • All dashboard.slice.ts RTK Query endpoints working against real /api/v1/plus/dashboard/* responses • Type mismatches reconciled (update types or add transform layers) • MSW mocks moved behind NEXT_PUBLIC_MOCK_DASHBOARD=true flag (not deleted) • Error states handled per endpoint (loading, error, empty data) • alphaDashboard feature flag still gates everything • No regressions on: PostureCard, PriorityActionsCard, DSRStatusCard, SystemCoverageCard, CommandBar, AgentBriefing | DASH-1 | §4 (all P1 components) | Pick up incrementally as DASH-1 endpoints land
DASH-3 | Phase 1: Backend Foundation & P1 Polish | [FE] P1 dashboard UI polish and refinements | Frontend | 5 | Visual quality, animation, and interaction polish on existing P1 components per PRD design philosophy. | • GPS score count-up animation on load • Action queue items slide in/out on completion (200-300ms ease-out) • Radar segments animate on hover • Dark mode audit: all P1 components render correctly, no contrast issues, data visualizations look striking • Whitespace and spacing pass — more generous than default Ant • Loading skeletons (not spinners) for each panel • Responsive behavior verified on smaller screens • Empty states designed for each component | None | §7 Visual Design | Can start immediately — no backend dependency
DASH-4 | Phase 2: New Dashboard Components | [BE] GPS expansion to 7 dimensions | Backend | 5 | Extend the posture service from DASH-1 with three new scoring dimensions: Policy Enforcement (15%), AI Readiness (10%), Assessment Coverage (10%). Also adds a dedicated AI Readiness summary endpoint for the executive panel. | Policy Enforcement (15% weight): • Scores on: % of systems with governing policy, policy violations from EventAudit, unresolved violation age • Systems without policy = 0 score; violations weighted by severity × age AI Readiness (10% weight): • Per-system: 5 binary criteria (classified, consent-bound, de-ID strategy, policy applied, PIA complete) • System readiness = criteria met / 5; aggregate = weighted avg across systems • GET /api/v1/plus/dashboard/ai-readiness returns: aggregate score, fully/partially/not ready counts, per-criterion rates Assessment Coverage (10% weight): • Queries PrivacyAssessment: activities without PIAs, overdue, in_progress >30 days • Score = covered / total, adjusted for overdue and stale All 7 dimensions re-weighted: Coverage 20%, Classification 15%, DSR 15%, Consent 15%, Policy 15%, AI Readiness 10%, Assessment 10% | DASH-1 | §3 Risk Framework / §4.6 AI Readiness | Extends posture service; AI Readiness endpoint also serves DASH-11
DASH-5 | Phase 2: New Dashboard Components | [BE] Activity feed and risk detection endpoints | Backend | 5 | Two related endpoints: the activity feed (maps EventAudit to a timeline) and risk detection (evaluates 8 risk dimensions into ranked cards). Both surface platform intelligence to the dashboard. | Activity Feed (GET /api/v1/plus/dashboard/activity-feed): • Paginated ActivityFeedResponse with ?page=, ?size=, ?start_date=, ?end_date= • Maps EventAudit → ActivityFeedItem: actor_type (human/system/agent), message, timestamp • Templates per event type: "Helios classified {count} fields...", "DSR-{id} completed..." • Filterable by category prefix; newest first; 90-day default Risk Cards (GET /api/v1/plus/dashboard/risks): • Ranked RiskCard list: severity, title, description, affected_systems, detected_at, action_type + action_data, agent_rationale (template V1) • Evaluates 8 dimensions: unreviewed classifications, unreviewed systems, overdue DSRs, no steward, unclassified systems, consent failures, policy violations, no PIAs • Severity = regulatory exposure × time sensitivity × blast radius • Deduplication across same system; top 10 cap (configurable) | None | §4.8 Activity Feed / §3 Risk Cards | Frontend types + RTK Query already defined for activity feed
DASH-6 | Phase 2: New Dashboard Components | [BE] Consent health, Astralis activity, and persona preference endpoints | Backend | 3 | Three smaller endpoints bundled: consent health metrics, Astralis agent activity, and user persona preferences. | Consent Health (GET /api/v1/plus/dashboard/consent-health): • active_consent_records count, monitoring_status (healthy/degraded/failing from EventAudit digest events) • anomaly_flags (opt-out deviations >2σ from 30-day rolling avg), consent_to_processing_alignment % • Anomaly threshold configurable Astralis Activity (GET /api/v1/plus/dashboard/astralis): • AstralisResponse: active_conversations (in_progress assessments), completed_assessments, awaiting_response (no AnswerVersion >3 days), risks_identified (risk_level > low) • Per-conversation: steward name, system, status, days since last activity Persona Preferences (GET/PATCH /api/v1/plus/dashboard/preferences): • Accepts persona: legal_privacy ¦ governance_grc ¦ data_engineer ¦ executive • Returns persona + default section ordering • Stored on user model (new column or JSONB) | None | §4.7 / §4.10 / §2 | Three lightweight endpoints — can split if team prefers
DASH-7 | Phase 2: New Dashboard Components | [FE] GPS radar chart expansion to 7 dimensions | Frontend | 3 | Update PostureCard and PostureBreakdownContent to render 7 dimensions instead of 4. | • Radar chart renders all 7 dimensions when returned by API • constants.ts dimension config updated with labels, colors, routes for Policy Enforcement, AI Readiness, Assessment Coverage • PostureBreakdownContent drawer shows all 7 with per-dimension action links • Graceful degradation if API returns fewer dimensions • No visual regressions on existing 4 dimensions | DASH-4 | §4.2 GPS | Can start against mocks; wire to real data later
DASH-8 | Phase 2: New Dashboard Components | [FE] Activity feed component | Frontend | 5 | Scrolling, filterable activity feed for the dashboard bottom tier. Makes the platform feel alive. | • Scrolling list with icon (by actor type), message, relative timestamp • Filterable by type: All / Human / System / Agent • Each item clickable — navigates to relevant detail view • New items fade in from top (200ms ease-out) • "Powered by Helios / Janus / Lethe / Astralis" attribution per item • Infinite scroll pagination • Empty state: "No recent activity" • MSW mock handler added | DASH-5 | §4.8 Activity Feed
DASH-9 | Phase 2: New Dashboard Components | [FE] Risk cards panel component | Frontend | 5 | Risk alert cards rendered between GPS/Actions row and middle tier panels. | • Cards follow PRD structure: severity icon + color, title, one-line description, affected systems count, action button, time since detected • Expandable agent rationale per card • Recommended action with pre-linked CTA • Severity colors: red (critical), orange (high), yellow (medium), blue (low) • Empty state: green check + "No active risks" • RTK Query endpoint + types in dashboard slice • MSW mock handler | DASH-5 | §3 Risk Cards
DASH-10 | Phase 2: New Dashboard Components | [FE] Consent health panel component | Frontend | 3 | Consent health card for the dashboard middle tier. | • Shows: active consent records, monitoring status indicator (green/amber/red dot), anomaly flag with description, consent-to-processing alignment % • Click-through to /consent/reporting • "Ask Astralis" button placeholder (disabled V1) • RTK Query endpoint + types added • MSW mock handler | DASH-6 | §4.7 Consent Health
DASH-11 | Phase 2: New Dashboard Components | [FE] AI Readiness panel component | Frontend | 5 | Executive-facing panel designed to be screenshot-worthy for CIO/CDO conversations. | • Aggregate AI Readiness score (large, animated number) • System breakdown: X fully ready / Y partial / Z not ready • 5-criteria visual checklist with completion rates per criterion • Click-through to detail view (drawer or page with per-system readiness) • "Ask Astralis" button placeholder • Works in both light and dark mode • MSW mock handler | DASH-4 | §4.6 AI Readiness | Design for screenshots — bold numbers, clear labels
DASH-12 | Phase 2: New Dashboard Components | [FE] Astralis agent activity panel component | Frontend | 5 | Shows AI agents actively conducting assessments in real-time. The PRD's "wow moment." | • Active conversations, awaiting response (overdue styling if >3 days), completed assessments, risks identified • Each metric clickable — opens list with steward name, system, status • Activity indicators, progress states, steward avatars • Click-through to PIA management view • Persistent agent status strip: "Active: X PIA conversations · Y auto-approvals ready" • RTK Query already exists — add mock handler • Works in dark mode | DASH-6 | §4.10 Astralis Panel | Should feel like watching a team of analysts working
DASH-13 | Phase 2: New Dashboard Components | [FE] Persona selector and adaptive dashboard ordering | Frontend | 5 | Role selection in settings + dashboard section reordering based on persona. | • Settings page: persona picker (Legal/Privacy, Governance/GRC, Data Engineer, Executive) • First-login modal if no persona set • Dashboard sections reorder by persona (all visible, priority changes): Legal elevates DSR + Consent, Governance elevates Classification + Systems + Policy, Engineer filters to owned systems, Executive shows summary mode • Quick Stats bar adapts pill content per persona • Persisted via DASH-6 persona endpoint | DASH-6 | §2 Persona Strategy
DASH-14 | Phase 2: New Dashboard Components | [FE] Notification bell | Frontend | 3 | Notification bell in CommandBar with unread count and dropdown panel. | • Bell icon with unread count badge in CommandBar • Dropdown panel showing recent alerts (from risk cards + critical action queue items) • Each notification clickable — navigates to detail view • "Mark all read" action • V1: notifications derived client-side from already-loaded dashboard data • Unread state in localStorage (V1) | None | §4.1 Command Bar | No backend dependency — client-side only
DASH-15 | Phase 2: New Dashboard Components | [FE] P2 component UI polish and refinements | Frontend | 5 | Polish pass on all new P2 components after initial implementation. | • Activity feed fade-in animations on new items • Risk card severity colors and icons consistent with design system • AI Readiness panel screenshot-ready in light + dark mode • All components match motion language: 200-300ms transitions, ease-out • Micro-interactions: hover states, expand/collapse, tab transitions • Cross-component visual consistency audit • Mobile/responsive spot-check | DASH-8 through DASH-13 | §7 Visual Design | Gates on P2 components having first pass done
DASH-16 | Phase 3: Steward Inbox | [BE] Steward inbox backend (aggregation, plain-language, deep links) | Backend | 8 | Full backend for the steward inbox: task aggregation from 4 sources, jargon-free plain-language explanations, and deep link support for external notification arrivals. | Task Aggregation (GET /api/v1/plus/steward/inbox): • Paginated tasks for authenticated user • Pulls from: StagedResource classifications (via MonitorSteward), ManualTaskInstance, PrivacyAssessment conversations, system info requests • Each task: type, urgency (urgent/this_week/when_ready), title, system name, due date, status • Urgency from: due date proximity × regulatory sensitivity × time since created • Completed tasks via ?status=completed; sorted: urgency → due date → created Plain-Language Explanations: • Each task includes plain_description and impact_statement • Templates per type: "Review the data labels for your CRM" not "Approve pending Fideslang classifications" • Impact: "If labels aren't confirmed within 5 days, system shows as unclassified" • V1: deterministic templates. V2: LLM-generated Deep Links (GET /api/v1/plus/steward/inbox/task/{taskId}): • Single task with full context (system details, field list, conversation history) • /steward-inbox?task={taskId} format • Auth handling for email/Slack arrivals within session expiry | None | §8 Steward Inbox | Can split into sub-tickets if team prefers
DASH-17 | Phase 3: Steward Inbox | [FE] Steward inbox shell and task list | Frontend | 8 | Page structure, routing, nav integration, urgency grouping, and common task card chrome shared by all four task types. | • New route /steward-inbox, added to sidebar nav • Urgency-grouped list: Urgent (red), This Week (amber), Review When Ready (blue) • Common task card: urgency badge, title, plain-language description, system name, due date, impact statement (expandable), primary action button • Completed tasks section (collapsible) with count • Deep link handling: ?task={id} auto-opens task • Empty state: celebration — "All clear!" • Mobile-responsive (single column, touch-friendly) • RTK Query integration with DASH-16 | DASH-16 | §8 Steward Inbox | Foundation for DASH-18 through DASH-21
DASH-18 | Phase 3: Steward Inbox | [FE] Classification review task type | Frontend | 8 | Most interaction-heavy task type. Field-by-field approve/edit/reject for detected data classifications. | • Inline or expandable detail panel: list of fields with suggested data categories • Per-field actions: approve (checkmark), edit (category picker), reject (required reason) • Batch approve for high-confidence (>95%): "Approve all?" • Field summary: "12 new fields detected, 8 auto-approved, 4 need review" • Shows field name, source table, suggested category, confidence score • Submit sends approvals/edits/rejections to classification system • Completion toast, task moves to completed | DASH-17 | §8 Steward Inbox | Complex per-field interaction UI
DASH-19 | Phase 3: Steward Inbox | [FE] DSR manual step task type | Frontend | 3 | Steward confirms a manual data action (usually deletion) has been completed. | • Shows: what was requested, which system, which identity, what action needed • Checkbox: "I confirm this data has been deleted from [System]" • Optional notes field • Warning if approaching SLA deadline • Submit sends confirmation to DSR pipeline | DASH-17 | §8 Steward Inbox
DASH-20 | Phase 3: Steward Inbox | [FE] PIA conversation task type | Frontend | 8 | Two-way conversation with Astralis within the inbox. The PRD's "conversation surface, not just a task list." | • Conversation history between Astralis and steward (from PrivacyAssessment + AnswerVersion) • Inline reply — text input submitting new AnswerVersion • Astralis questions as chat bubbles with "what's being asked" and "why it matters" • External handoff links to Slack/Teams if configured • Assessment progress: "Question 3 of 8 answered" • Previous answers editable | DASH-17 | §8 Steward Inbox | Chat-style UI with AI agent — significant complexity
DASH-21 | Phase 3: Steward Inbox | [FE] System information request task type | Frontend | 5 | Guided form for stewards to provide/update system metadata. | • Fields: data categories processed, retention period, third-party sharing, processing purposes • Pre-filled suggestions from existing system metadata + Astralis inference • Plain-language helper text per field • Progressive disclosure: required fields first, optional behind expander • Validation with helpful errors • Submit updates system record via existing system API | DASH-17 | §8 Steward Inbox

## Summary
Phase / Epic | Tickets | Backend Pts | Frontend Pts | Total Pts
Phase 1: Backend Foundation & P1 Polish | 3 | 8 | 10 | 18
Phase 2: New Dashboard Components | 12 | 13 | 39 | 52
Phase 3: Steward Inbox | 6 | 8 | 32 | 40
Total | 21 | 29 | 81 | 110